## Joint States Yr 3 Workplan
| S/N | Component/Function/Event | Recipient | Delivery Method, Adviser | PREMIS Output Activity | Priorities HSS | Priorities SWS | Priorities GSS | Priorities JSS | April 2019 | May 2019 | Jun 2019 | Jul 2019 | Aug 2019 | Sep 2019 | Oct 2019 | Nov 2019 | Dec 2019 | Jan 2020 | Feb 2020 | Mar 2020 | Total Nairobi Based Workshops | Total State-based Workshops (Combined) | Total State-based Workshops (Separate) | CAT 1 | CAT 2 | CAT 3 | QTR | Expected Example Outputs |  | Workshop or Training Event (Nairobi) | Ongoing TA | Category 1 Structured Mentoring | Category 2 State-based Training Event Separate | Category 3 State-based Training Event Combined | Procurement (SPG or PREMIS)
Public Financial Management
| 1 | Macro Fiscal and Policy
| 1.a | Tax Policy
| 1.a.1 | Annual Joint Tax Policy and Law Review and refresher training | All FMS RCA and Customs and Tax Policy | Joint Workshop, Revenue Adviser | 3.1 | Medium | Very High | Very High | [13 empty] | 1 | - | - | - | - | -
| 1.b | Revenue Management
| 1.b.1 | Annual Joint Organisational and Management Review. | All FMS RCA and Customs and Tax Policy | Joint Workshop, Revenue Adviser | 3.2 | High | High | Moderate | [13 empty] | 1 | - | - | - | - | -
Combined together in Nairobi whereby 1.b.4 was a combined state based is now a Nairobi based running back to back with 1.b.3 and 1.b2 | 1.b.2 | Tax Administration using RMS and FMIS, Super User Training, Annual Revenue Enhancement Planning and Estimation | All FMS RCA and Customs and Tax Policy | Joint Workshop, Revenue Adviser | 3.3 | Very High | High | High | [13 empty] | 1 | - | - | - | - | -
| 1.b.5 | Regular Induction and Refresher Training for New Recruits and Agents | FMS RCA, Customs and Policy | State-based Workshop, In-Country Revenue Adviser | 3.2 | Medium | High | Very High | Very High |  | GSS | JSS | SWS |  |  |  | HSS |  |  |  |  | - | - | 4 | 4 | - | -
Removed JSS | 1.b.6 | Property Tax Registration, State and District | FMS RCA, Customs and Policy | State-based Workshop, In-Country Revenue Adviser | 3.3 | Very High |  | Very High | Medium |  |  |  |  | HSS | GSS | [6 empty] | - | - | 2 | - | 2 | -
| 1.b.7 | On-going Technical Assistance for Re-drafting Laws, revising Policies, Supporting revenue enhancement, Toolbox maintenance and Property Tax registration, | FMS RCA, Customs and Policy | Revenue Adviser, In-Country Revenue Advisers | 1.1 | High | High |  | Very High | [12 empty] | - | - |  | - | - | -
| 1.b.8 | To acquire and implement POS device at the collection points in order to print payment receipt -- all FMS. | FMS RCA, Customs and Policy | Competitive Procurement, Revenue Adviser, ICT Adviser, Procurement Adviser | 3.7 | Very High | High | Very High | Very High | [12 empty] | - | - |  | - | - | -
| 1.c | Macroeconomic and Fiscal Policy Planning & Analysis
| 1.c.1 | Contribute to increased interpretation and analysis of historical revenue and expenditure information within FMS MFUs through the development of quarterly Fiscal Outturn Analyses | All FMS Macro-Fiscal units | Workshop, Ongoing TA | 2.2 | Very High | High | High | High | [6 empty] | C JSS SWS GSS HSS | [5 empty] | - | 1 | - | - | - | 1
| 1.c.2 | Support the development of the Annual Budget Framework Paper and Budget Speech | All FMS Macro-Fiscal units, Ministry of Planning | Workshop, Ongoing TA, Macro fiscal Adviser | 1.4 | High | High | Very High | Very High | [12 empty] | - | - | - | - | - | -
| 1.c.3 | Support the development of at least 1 fiscal impact analysis report introducing new legislation or proposed changes to the tax policy | All FMS Macro-Fiscal units | Workshop, Ongoing TA, Competitive Procurement | 1.4 | Very High | High / Procurement Medium | High | Very High |  |  |  | C JSS SWS GSS HSS | [8 empty] | - | 1 | - | - | - | 1
| 1.c.4 | Develop quantitative analysis and Excel skills to support macroeconomic and fiscal analysis | All FMS Macro-Fiscal Units | Microsoft Series - (E-learning delivered via EDX.org) | 1.4 | Very High | High | Very High | Very High | [12 empty] | - | - | - | - | - | -
| 1.c.5 | Develop Memorandum of Understanding regarding Data Collection and Sharing between the FGS and each FMS | All FMS Macro-Fiscal units; FGS MoF | Ongoing TA | 1.4 | Medium | High |  | High | [12 empty] | - | - | - | - | - | -
| 1.c.6 | Provide on-request support to FMS Macro-Fiscal Units with regards to the development of State Development Plans or other topics as agreed with PREMIS management | All FMS Macro-Fiscal units | Ongoing TA | 1.4 | Medium | High |  | Very High | [12 empty] | - | - | - | - | - | -
| 1.c.7 | Conduct final training on macro-fiscal analysis and economic modelling, and close-out support | All FMS Macro-Fiscal units | Workshop, Macro fiscal Adviser | 1.4 | Very High | High | Moderate | Very High | [12 empty] | 1 | - | - | - | - | -
| 2 | Budget Preparation
| 2.a | Preparation Policies and Procedures
From Combined to State based Cat 1 | 2.a.1 | Refresher Training for BPM Super User | BPM Super User | Structured Mentoring conducted by FA, GSS, SWS, Systems Adviser and Training Specialist | 1.4 | Very High | High | Very High | Very High |  |  | S JSS SWS GSS HSS | [9 empty] | - |  | 4 | 4 | -
| 2.a.2 | Prior to the commencement of the Budget Cycle, provide training to all BPM User | FMS MDA's & Budget Department | Training - BPM Super Users, Systems Adviser and Training Specialist | 1.4 | High |  | Very High | Very High | [12 empty] | - | - |  |  | - | -
| 2.a.3 | Meeting with Revenue Department, MFU, EAFS to obtain revenue estimates and discuss the commencement of the Budget Preparation Cycle | Budget Dept, Revenue Dept, MFU, EAFS Unit | Meeting | 1.4 | Medium |  |  | High | [12 empty] | - | - | - | - | - | -
| 2.a.4 | Budget Workshop to commence the Budget Process | All FMS MDA's | Workshop, Financial Advisers | 1.4 | Medium |  | Very High | Very High |  |  |  | S JSS SWS GSS HSS | [8 empty] | - | - | 4 | - | 4 | -
| 2.a.5 | Preparation of Supplementary Budget and Temporary Budget | MoF Budget department | Financial Advisers, On-the-job training | 1.4 | High |  |  | High | [12 empty] | - | - | - | - | - | -
| 2.b | BPM Operation
| 2.b.1 | Provide ongoing assistance to the BPM Super User to provide in-house training & Support to BPM Users as and when required. | FMS BPM Super Users | Systems Adviser and Training Specialist, On-the-job training | 1.4 | Very High |  |  | Very High | [12 empty] | - | - | - | - | - | - |  | TA support to Super User and ensure the Super User provides training to BPM Users as and when required
| 3 | Budget Execution
| 3.a | Tax Administration
| 3.a.1 | Property Tax Survey and house numbering HSS (Continuation from Year2) | HSS Revenue Collection Authority | Competitive Procurement | 3.4 | Very High | [15 empty] | - | - | - | - | - | -
| 3.a.2 | Property Tax Survey and House numbering GSS (Continuation from Year 2) | GSS Revenue Collection Authority | Competitive Procurement | 3.4 |  |  | Very High | [13 empty] | - | - | - | - | - | -
| 3.a.3 | Construct and Equip Four Revenue Checkpoint Huts in each FMS, including provision of Solar Power (Continuation from Year 2) | FMS RCA | Competitive Procurement | 3.7 | High | High | Very High | Very High | [12 empty] | - | - | - | - | - | -
| 3.a.4 | Upgrading and Development of Revenue Toolbox. Procurement of System Development to migrate Toolbox. (continuation form Year 2) | All FMS RCA | Shopping, Procurement Adviser | 3.3 | Very High | High | Very High | Very High
| 3.a.5 | Communication campaign, Business Assessment and Market Survey | All FMS RCA | Shopping, Revenue Adviser, Procurement Adviser | 3.5 | High | High | Very High | Very High | S HSS JSS | GSS | [5 empty] | SWS |  |  |  |  | - | - | - | - | - | -
| 3.a.6 | Communication and awareness campaigns in districts GSS | GSS | Shopping, Revenue Adviser, Procurement Adviser | 3.5 |  |  | Very High |  |  |  | GSS |  |  |  |  | GSS |  |  | GSS |  | - | - | - | - | - | -
| 3.a.7 | Communication and awareness campaigns in districts HSS | HSS Revenue Collection Authority | Shopping, Revenue Adviser, Procurement Adviser | 3.5 | Very High |  |  |  | HSS |  |  |  | HSS |  |  |  |  | HSS |  |  | - | - | - | - | - | -
| 3.a.8 | Communication and awareness campaigns in districts JSS | JSS | Shopping, Revenue Adviser, Procurement Adviser | 3.5 |  |  |  | Very High |  |  | JSS |  |  |  |  | JSS |  |  | JSS |  | - | - | - | - | - | -
| 3.a.9 | Communication and awareness campaigns in districts SWS | SWSS | Shopping, Revenue Adviser, Procurement Adviser | 3.5 |  | High |  |  |  |  | SWSS |  |  |  |  | SWSS |  |  | SWSS |  | - | - | - | - | - | -
| 3.a.10 | Communication. Meeting with LNGOs, INGOs and Private Companies operating within GSS to inform TCC requirement for contract award | GSS | Shopping, Revenue Adviser, Procurement Adviser | 3.5 |  |  | Very High |  |  | GSS | GSS | [9 empty] | - | - | - | - | - | -
| 3.a.11 | Communication Campaign on Khat and Cigarette Taxation. | GSS, SWS, HSS | Shopping, Revenue Adviser, Procurement Adviser | 3.5 | High | Medium | Very High | [5 empty] | S GSS SWS | [7 empty] | - | - | - | - | - | -
| 3.a.12 | Communication campaign over 3-month to increase awareness on the duties the citizens owe to the state by paying taxes in time. This is in turn expected to increase the level of voluntary compliance. | All FMS RCA | Shopping, Revenue Adviser, Procurement Adviser | 3.5 | Medium | Medium | Very High | Very High | [5 empty] | S GSS SWS |  |  |  |  | S HSS JSS |  | - | - | - | - | - | -
| 3.a.13 | Taxpayer communication campaigns | JSS | Shopping, Revenue Adviser, Procurement Adviser | 3.5 |  |  |  | Very High |  |  | JSS | [6 empty] | JSS |  |  | - | - | - | - | - | -
| 3.a.15 | Rollout of Collection: Communication, Registration, RMS training | FMS RCA, Customs and Policy | State-based Workshop, In-Country Revenue Adviser | 3.3 | Medium | High | Very High | Very High |  |  |  | S GSS SWS |  |  |  | HSS |  |  | JSS |  | - | - | - | - | - | -
| 3.a.17 | Tax Administration: Air and sea ports; Customs, Khat, and Cigarettes; Road User Taxes; NGOs and Corporations; Livestock and Resource Taxation; Vehicles | FMS RCA, Customs and Policy | State-based Workshop, In-Country Revenue Adviser | 3.3 | Medium | Medium | Very High | Medium | [5 empty] | S JSS HSS | SWS |  | GSS |  |  |  | - | - | 4 | 4 | - | -
| 3.a.18 | Tax Administration: Disputes & Compliance Management | FMS RCA, Customs and Policy | State-based Workshop, In-Country Revenue Adviser | 3.6 | High | High | Very High | Medium |  |  |  | GSS |  |  | SWS | S JSS HSS |  |  |  |  | - | - | 4 | 4 | - | -
| 3.a.22 | Tax Administration: Organisation Development | FMS RCA, Customs and Policy | State-based Workshop, In-Country Revenue Adviser | 3.2 | Medium | Medium | Moderate | Very High |  |  |  |  | HSS | SWS |  |  |  | GSS | JSS |  | - | - | 4 | 4 | - | -
| 3.a.24 | Support the establishment and training of Tax Appeals Board | FMS RCA, Customs and Policy | State-based Workshop, In-Country Revenue Adviser | 3.3 | Medium | High | Very High | High | [8 empty] | GSS | S SWS JSS | HSS |  | - | - | 4 | 4 | - | -
| 3.b | Procurement
| 3.b.1 | Works Contract management Training | All FMS Procurement Departments | Workshop, Procurement Advisers | 1.4 | Very High |  | Very High | Very High |  |  | C JSS SWS GSS HSS | [9 empty] | - | 1 | - | - | - | 1
| 3.b.2 | Implement Annual Maintenance and Support Agreement (AMSA) for ICT equipment, install Windows 10 and Microsoft 2019. Asset Management and Tagging Review | All FMS Procurement Departments | Workshop, Procurement Advisers | 1.4 | High |  | Very High | High | [12 empty] | - | - | - | - | - | -
Moved from Combined to State based Cat 2 | 3.b.3 | Procurement Training 101 for new Procurement Officers -- including TTT approach. Public Procurement Training initiative to selected MDAs | All FMS Procurement Departments | Workshop, Procurement Advisers | 1.4 | Medium |  | Moderate | High |  |  |  |  | S GSS HSS |  | S JSS SWS | [5 empty] | - | - | 4 | - | 4 | -
| 3.b.5 | Public Procurement Training - Prequalification Process and Supplier Data Base. Basic Training initiative to selected MDAs | All FMS Procurement Departments | Workshop, Procurement Advisers | 1.4 | High |  | High | Very High |  |  |  |  | S HSS | S GSS | S JSS | S SWS |  |  |  |  | - | - | 4 | - | 4 | -
| 3.b.6 | Support the establishment of Procurement Boards | All FMS Procurement Departments | Workshop, Procurement Advisers | 1.4 | Medium |  | High | High |  |  |  |  | S HSS | S GSS | S JSS | S SWS |  |  |  |  | - | - | 4 | 4 | - | -
| 3.b.7 | Update of Procurement Regulation and Standard Bidding Documents Instruction plus advanced procurement methods training | All FMS Procurement Departments | Workshop, Procurement Advisers | 1.1 | Medium |  | Very High | Very High | [12 empty] | 1 | - | - | - | - | -
| 3.b.9 | Ongoing support in relation to implementation of State based Procurement Policies and Procedures | All FMS Procurement Departments | Procurement Advisers, ICT Adviser | 1.4 | Very High |  |  | High | [12 empty] | - | - | - | - | - | -
| 3.c | Banking Arrangements
| 3.c.1 | Revisit banking arrangements in SWS & determine if a banking services procurement is warranted. If required, provide assistance to SWS Procurement Dept. as required | SWS MoF | Systems Adviser, Procurement Adviser | 1.5 | [16 empty] | - | - | - | - | - | -
| 3.d | FMIS Operation
| 3.d.1 | Provide ongoing assistance to the FMIS Users. | FMIS Super Users | On-the-job training, FMS Super User network, Systems Adviser and Training Specialist | 1.4 | Very High |  |  | Very High | [12 empty] | - | - | - | - | - | -
| 3.e | PFM Operational Support
| 3.e.1 | Establish induction training program for new recruits | New recruits of MoF / Finance staff of MDA' | Treasury Director, Budget Director, Super Users, In-Country Adviser, TA support | 1.4 | Very High |  |  | Very High | [12 empty] | - | - | - | - | - | - |  | Induction program established (PFM component) , new recruits formally inducted
| 3.e.2 | PFM Training to EAFS Department / assigned Treasury Department Staff in relation to Donor Funds recording and management | EAFS, designated Treasury Staff | PFM International, In-Country Financial Advisers, Senior Systems Specialist, CS Advisers | 1.4 | Very High |  | High | High | S JSS SWS GSS |  | S HSS | [9 empty] | - | - | 4 | - | 4 | -
| 3.e.3 | Extension of office rent for MOF(ED) & CSCs & OAGs | GSS, HSS MOFED GSS, HSS CSC GSS OAG | SS Procurement, Procurement Adviser | 1.6 | Very High |  | Very High |  |  |  |  | HSS GSS | [8 empty] | - | - | - | - | - | -
| 4 | Accounting and Reporting
| 4.a.1 | Treasury Management
| 4.a.1 | Budget Classification Structure Management (GFS) | MoF | State Workshop, on-going TA support, International Advisor (remote assistance) | 1.4 | Very High |  | High | Very High |  |  | S JSS SWS GSS HSS | [9 empty] | - | - | 4 | 4 | - | -
| 4.a.2 | IPSAS Financial Statement Training. Working Paper training, compilation of work papers and supporting documentation. Understanding of the audit process | MoF, Internal & External Audit | State Workshop, on-going TA support, International Advisor (remote assistance). | 1.4 | Very High |  | Very High | Very High | [8 empty] | C JSS SWS GSS HSS |  |  |  | - | 1 | - | - | - | 1
| 4.a.3 | Document management (proper logical filing systems for ease of reference back to FMIS) | MoF Treasury, Budget, Revenue Depts. Internal Audit | State Workshop, on-going TA support, International Advisor (remote assistance) | 1.4 | Very High |  | High | Very High |  |  | S JSS SWS GSS HSS | [9 empty] | - | - | 4 | - | 4 | -
| 4.a.4 | Provide ongoing technical support in relation to the implementation of recommendations resulting from the annual Audit | All FMS Treasury Departments | ongoing TA support | 1.4 | High |  |  | Very High | [12 empty] | - | - | - | - | - | -
| 4.a.5 | Launch Public Financial Management (PFM) Communication Campaign | HSS MoFED- Office DG | Shopping, Procurement Adviser | 1.6 | Very High |  | Very High |  |  |  |  | HSS GSS SWS | [8 empty] | - | - | - | - | - | -
| 5 | Audit
| 5.a | External Audit
Moved from Combined to State based Cat 1 | 5.a.1 | New civil servants introduction Training | New Auditors from HSS and JSS | State Based workshop, External Audit Advisor, Financial Adviser | 2.3 | High | High |  | High |  |  | S JSS HSS | [9 empty] | - |  | 2 | 2
| 5.a.2 | Audit Introductory and Planning workshop | New Auditors from HSS and JSS | State Based workshop, External Audit Advisor, Financial Adviser | 2.3 | High | High |  | High |  |  |  | S JSS HSS | [8 empty] | - |  | 2 | 2 | -
| 5.a.3 | Audit Execution/Reporting Training | New Auditors from HSS and JSS | State Based workshop, External Audit Advisor, Financial Adviser | 2.3 | High | High |  | High |  |  |  |  | S JSS HSS | [7 empty] | - |  | 2 | 2 | -
| 5.a.4 | Advanced audit training for all FMS | GSS,SWS,JSS and HSS Auditor General Offices | External Audit Advisors. Workshop | 2.3 | High | High | Very High | High | [12 empty] | 2 | - | - | - | - | -
| 5.a.5 | Final/Strategic Planning Workshop | GSS,SWS,JSS and HSS Auditor General Offices | Workshop. External Audit Advisors. | 2.3 | High | High | Very High | High | [12 empty] | 1 | - | - | - | - | -
| 5.a.6 | Compliance audit manual workshop with Federal OAG – Oct 2019 | GSS,SWS,JSS and HSS Auditor General Offices. Federal AG | Workshop. External Audit Advisors, IDI. | 2.3 | High | High | Very High | High | [12 empty] | 1 | - | - | - | - | -
| 5.a.7 | Sensitisation of MDAs and Politicians on role and responsibilities of OAGs | GSS,SWS,JSS and HSS Auditor General Offices | 1 State based Communication event in each state. To be held in capitals of each state. | 2.3 | Moderate | Moderate | High | Moderate | [12 empty] | - | - | - | - | - | -
| 5.a.9 | On going Technical Assistance | GSS,SWS,JSS and HSS Auditor General Offices | On site and remote assistance and coaching-November -state based workshops on State Legal Frame work | 2.3 | High | High | Moderate | High | [7 empty] | S HSS GSS |  | S JSS SWS |  |  | - | - | 4 | 4 | - | -
| 5.a.10 | Technical Assistance on two special audits in each FMS | GSS,SWS,JSS and HSS Auditor General Offices | On site guidance and coaching | 2.3 | High | High | High | High | [12 empty] | - | - | - | - | - | -
| 5.a.11 | Procurement of private sector audit firm for support to procurement audit in the 4 FMS. | GSS,SWS,JSS and HSS Auditor General Offices | Competitive Procurement, External Audit Adviser | 2.3 | High | High | High | High | [12 empty] | - | - | - | - | - | -
| 5.a.12 | Support to FMS Audit FY 2018 | GSS,SWS,JSS and HSS Auditor General Offices | On site and remote assistance and coaching | 2.3 | High | High | High | High | [12 empty] | - | - | - | - | - | -
| 5.a.13 | Audit Report Publication Launch and Communication | GSS,SWS,JSS and HSS Auditor General Offices | Publication of FY 2017 (JSS,GSS and SWS) and FY 2018 (JSS,GSS,SWS and HSS). Launch event | 2.3 | High | High | High | High | [12 empty] | - | - | - | - | - | -
| 5.a.14 | Procurement of private sector audit firm (working with State Audit Office Staff) for GSS, SWS, JSS and HSS Audit FY 2018 (Continuation from Year 2) | GSS,SWS,JSS and HSS Auditor General Offices | Single Source Procurement | 2.3 | High | High | Very High | High | [12 empty] | - | - | - | - | - | -
| 5.a.15 | Translation and Printing of FY 2018 BTM Audit Reports, Management letters and FY 2018 annual Audit Report for GSS,HSS,SWS and JSS. | GSS,SWS,JSS and HSS Auditor General Offices | Shopping, Procurement Adviser | 2.3 | High | High | Very High | High | [12 empty] | - | - | - | - | - | -
| 5.a.16 | Office Rent and Equipment | JSS OAG | Competitive Procurement, Procurement Adviser. | 2.5 | High | High | High | High | [12 empty] | - | - | - | - | - | -
| 5.a.18 | Provision of Laptops | HSS and JSS OAGs | IDIQ Procurement, Procurement Adviser | 2.3 | High | High | High | High | [12 empty] | - | - | - | - | - | -
| 5.b | Internal Audit
| 5.b.1 | Continuing Capacity Development for practical Auditing and review of specific internal audits in each FMS Ministry of Finance | All FMS MoF Internal Audit Departments | Workshop, Ongoing TA support, Internal Audit Advisers | 2.1 | Very High |  | High | Very High | [6 empty] | C JSS SWS GSS HSS |  |  |  |  | C JSS SWS GSS HSS | 1 | 2 | - | - | - | 2
converted to TA support | 5.b.2 | Developing a professional approach to the work of internal audit, enhance network with the Institute of Internal Auditors Kenya through IIA Kenya conference | All FMS MoF Internal Audit leaders including national audit adviser | Conference -- IIA Kenya | 2.1 | High |  | Very High | Very High | [13 empty] | - | - | - | - | -
| 5.b.3 | Procurement for part time IT audit consultant to assist with the workshop (October) and lead/oversee the IT audits. | All FMS MoF Internal Audit Departments | Temporary Ongoing TA | 2.1 | High |  | High | High | [12 empty] | - | - | - | - | - | -
| 5.b.4 | Improving the knowledge of internal controls in each FMS Ministry of Finance through Control self-assessment | All FMS MoF Procurement, Treasury, Revenue and HR Departments | Workshops, Internal Audit Adviser and respective Adviser | 2.1 | Very High |  | Very High | High |  |  |  | JSS | SWS |  |  | GSS | HSS |  |  |  | - | - | 4 |  | 4 | -
| 6 | Cross cutting Issues
| 6.a | Legal Framework
| 6.a.1 | Education & interpretation workshops across functioning MDAs regarding FMS PFM and PA Legislative Framework, including coverage of all Acts, Regulations and Instructions | All functioning MDAs | Workshops | 1.1 | High |  | Very High | Very High |  |  | S JSS SWS GSS HSS | [9 empty] | - | - | 4 | - | 4 | - |  |  | requested by GSS & SWSS, consider relevant for al FMS
| 6.b | Regulations
| 6.b.1 | Creating donor reporting awareness with Donors, MDA's and Banks | donors, MDA's | Treasury Department, FMS FA's | 1.4 | Very High |  | Very High | Very High |  |  |  |  | S JSS SWS GSS HSS | [7 empty] | - | - | - | - | - | -
| 6.b.2 | Review of Regulations and Instructions. | MoF | In-Country Financial Adviser, MoF Director General, Treasury Director | 1.1 | Very High |  |  | Very High | [12 empty] | - | - | - | - | - | - |  | Regulations & Instructions reviewed and updated
| 6.c | ICT
| 6.c.1 | Implementation of PFM Computer Training Centre (Continuation from Year 2) | All FMS MDAs | Competitive procurement, ICT Adviser, Systems Adviser, Procurement Adviser | 1.6 | High |  | Very high | Very High | [12 empty] | - | - | - | - | - | -
| 6.c.4 | Maintenance Support Agreement for ICT Equipment in each FMS (Continuation from Year 2) | All FMS MoF | Shopping, ICT Adviser, Procurement Adviser | 1.6 | Very High |  | Very High | Very High | [12 empty] | - | - | - | - | - | -
| 6.c.5 | Computer replacement | All FMS Procurement Departments | Competitive Procurement, ICT Adviser, Procurement Adviser | 1.6 | Very High |  | Very High |  | JSS | HSS | GSS | SWS | [8 empty] | - | - | - | - | - | -
| 6.d | Security Sector and Payroll Reform
| 6.d.1 | Conduct field visit in Galmudug with the objective of understanding security sector payroll procedures with a view to setting out options for automation and reform. | GSS Ministry of Interior and Security, Ministry of Finance | Field Visit. Country Team Leader, HR Adviser | 2.5 | [16 empty] | - | - | - | - | - | -
| 6.d.2 | Support all existing donor funded police personnel in one or two FMS to open a bank accounts where the government TSA is located. | GSS Ministry of Interior and Security and Ministry of Finance | Ongoing TA support, Country Team Leader and HR Adviser | 2.5 | [16 empty] | - | - | - | - | - | -
| 6.d.3 | Develop a budget model to prepare accurate wage budget for the security sector in 2020. This will be linked with the budget preparation for FY2020. | GSS Ministry of Interior and Security and Ministry of Finance | Workshop, Ongoing TA support, SS Adviser, Budget Execution Adviser, Financial Advisers, Country Team Leader, HR and CS Adviser | 1.4 | Medium |  | Very High |  |  |  |  | S JSS SWS GSS HSS | [8 empty] | - | - | 4 | 4 |  | -
| 6.e | MDA PFM and PA Devolution Training
| 6.e.1 | Support training for any newly devolved MDAs on FMIS/BPM/RMS as required, in conjunction with FMS Treasury & Budget Departments. | MDA finance departments | Workshop, Financial Adviser, Senior Financial Adviser and Training Specialist. | 1.2 | Very High |  | Very High |  |  |  |  | SWS | GSS | [7 empty] | - | - | 2 | - | 2 | - |  | PFM Devolved to key MDA's. MDA staff trained
Public Administration (CSC)
| 7 | Recruiting Activities
| 7.a | Recruiting Procedures
| 7.a.1 | Provide continued support on recruitment processes, procedures and monitoring. Ensuring all staff have required skills to analyse jobs, write job descriptions and interview effectively | All CSC Staff | Ongoing TA, HR and CS Adviser | 4.1 | Very High | High |  | Medium | [12 empty] | - | - | - | - | - | -
| 7.a.2 | Ensure that new CSC staff are taken through the full induction process including being made fully aware of recruitment regulations, procedures and processes | All CSC Staff | Ongoing TA, HR and CS Adviser | 4.1 | Very High | High |  | Medium | [12 empty] | - | - | - | - | - | -
| 8 | Civil Service Administration
| 8.a | CS Act and Regulations
| 8.a.1 | Training for all HR Directors Across FMS Ministries in CSC/CS Acts and Regulations. | TBC FMS Ministry HR Directors | CSC staff, HR and CS Advisers | 4.1 | Very High | High | Very High | High |  |  | S JSS SWS | S GSS HSS | [8 empty] | - | - | 4 | 4 | - | -
| 8.a.2 | Launching of CS and CSC Acts. | 80 Ministries, Civil Servants, Civil Society, FMS Representative | CSC Team and HR and CS Advisers | 2.1 | Very High | Very High | Very High | High |  |  | SWS HSS & GSS | JSS | [8 empty] | - | - | - | - | - | -
| 8.a.3 | Conduct communication campaign for the public on CSC roles and the importance of CS & CSC Act | 100 FMS Community, citizens | CSC Team and HR and CS Advisers | 4.1 | Very High | Medium | Very High | Medium |  |  | SWS | JSS | GSS | HSS | [6 empty] | - | - | - | - | - | -
| 8.a.4 | Ensure Human Resource personnel across MDAs of FMS are aware of the CS and CSC Acts and Regulations of the Civil Service Commission and conform to the application of the legislative frameworks. | All CSC and MDA HR Departments | Ongoing TA, HR and CS Adviser | 4.1 | Very High | Medium |  | Medium | [12 empty] | - | - | - | - | - | -
| 8.b | Institutional Structures and Processes
| 8.b.1 | Conduct CSC staff appraisal systems training | CSC Directors and officers | HR and CS Adviser | 4.1 | Very High | High | Very High | High | C SWS JSS |  | C HSS GSS | [9 empty] | - | 2 | - | - | - | 2
| 8.b.2 | Support the Civil Service Commission in the implementation of the Staff Appraisal System including ToT of CSC Staff | All CSC Staff | Ongoing TA, HR and CS Adviser | 4.1 | Very High | High |  | Medium | [12 empty] | - | - | - | - | - | -
| 8.b.3 | Support the Civil Service Commission in staff training and development plan so that all line Ministries have annual training planning. | All CSC staff | Ongoing TA, HR and CS Adviser | 4.1 | Very High | High |  | Medium | [12 empty] | - | - | - | - | - | -
Changed to CAT 1 | 8.b.4 | Secretarial Skills. | CSC staff | HR and CS Adviser | 4.1 | Very High | Medium | Moderate | High | [5 empty] | S HSS GSS |  | S SWS JSS |  |  |  |  | - |  | 4 | 4 | 0
| 8.b.5 | Provision of coaching, mentoring and on job training support to all CSC staff during office normal working hours | All CSC staff | Ongoing TA, HR and CS Adviser | 4.1 | Very High | Medium |  | Medium | [12 empty] | - | - | - | - | - | -
Moved from Combined to State Based Cat 2 | 8.b.6 | Training for Managing Staff conflicts, conduct, discipline and grievance | CSC Commissioners & HR Directors | HR and CS Adviser. Requirement for Train the Trainer prior to delivery so will add on to 8.b.12 | 4.1 | Very High | Very High | Very High | High |  |  | S SWS GSS |  | S HSS JSS | [7 empty] | - |  | 4 | - | 4
| 8.b.7 | Joint workshop for CSC and Ministry of Labour all FMS | Commissioners, Minister for Labour, DG | International Advisers | 4.1 | High | Very High | Very High | High | [12 empty] | 1 | - | - | - | - | -
| 8.b.9 | Newly recruited DGs induction Training and PFM orientations HSS, GSS | Recruited DGs | International Advisers, CTL and In-Country Adviser | 4.1 | Very High | Very High | Moderate | High | [12 empty] | 0 | - | - | - | 2 | -
| 8.b.10 | Interview skills training for the CSC staff. | CSC Staff | HR and CS Advisers | 4.1 | Medium | Very High | Moderate | High | [6 empty] | S JSS GSS |  | S SWS HSS |  |  |  | - | 2 | - | - | 4 | 0
| 8.b.11 | Refresher training for Joint CSC and Parliament Social Committee and Ministry of Labour | Commissioner Secretariat, Minister for Labour, Parliament Social Committee | International Advisers, In-Country Adviser | 4.1 | Very High | Very High | Very High | High | [12 empty] | 1 | - | - | - | - | -
| 8.b.12 | Introduction to Management Training Programme to introduce participants to all aspect of management and leadership -- All FMS | Commissioners and directors | International Adviser. To include Train the trainer of local Advisors | 4.1 | Very High | Very High | Very High | High | [12 empty] | 2 | - | - | - | - | -
| 8.b.13 | Women in Government Programme. Supporting women to realise their potential by enhancing their skills and abilities, challenge power and equality, whilst building confidence, assertiveness and self esteem. All FMS | Female Commissioners, Management level women in government | International Adviser | 4.1 | Very High | Very High | Very High | High | [12 empty] | 2 | - | - | - | - | -
| 8.b.14 | Support CSC in the implementation of the Exit interview system. Provide TA to monitor progress and application. | All FMS CSC. | In-Country HR and CS Advisers. | 4.2 | Very High | High | High | Medium | [12 empty] | - | - | - | - | - | -
| 9 | Cross Cutting Issues
| 9.b | Accredited Training Programme
| 9.b.1 | Review and Agree Selection Criteria (with FMS MoF). Shortlist and Select target Civil Servant using approved Selection Criteria (Training Agreement). | FMS MoF Civil Servants | Relevant Adviser. (PREMIS developed Selection Criteria with FMS CSC). | 1.6 | Very High |  |  | Very High | [12 empty] | - | - | - | - | - | -
| 9.b.2 | Contract Accredited Training providers for selected Civil Servants from each FMS (Continuation from Year 2) | FMS Civil Servants | External Provider Agreement -- SS | 1.6 | Very High |  | Very High | Very High | [12 empty] | - | - | - | - | - | -
| 9.b.3 | Support Accredited Training Programme in the enrolment of selected Civil Servants on PFM related courses from each FMS. | FMS Civil Servants | External Providers contracted by PREMIS | 1.6 | Very High |  |  | High | [12 empty] | - | - | - | - | - | -
| 9.b.4 | Mentoring of Civil Servants enrolled for PFM related course. Provide continuing support to the Programme | FMS Civil Servants. | Ongoing TA support, Relevant Adviser | 1.6 | Very High |  |  | High | [12 empty] | - | - | - | - | - | -
| 9.c | HRMIS
| 9.c.1 | Acquire and implement a Human Resource Management Information System (HRMIS) for implementation in each FMS CSC (Continuation from Year 2) | All FMS CSC | Competitive procurement, ICT Adviser, HR and CS Adviser, System Adviser, Procurement Adviser | 4.2 | Very High | High | Very High | High | [12 empty] | - | - | - | - | - | -
| 9.c.2 | Develop HRMIS implementation plan, conduct system pilot rollout configuration . | System vendor, FMS CSC and PREMIS Advisors. | System vendor and relevant PREMIS Advisors. | 4.2 | Very High | High |  | Medium | [12 empty] | - | - | - | - | - | -
| 9.c.3 | Conduct system User training workshops followed by on-going TA across all aspects of HRMIS implementation, including functionality review as and when required. | All FMS CSC System Super User. | System supplier and relevant PREMIS Advisors. | 4.2 | Very High | High | Very High | Medium | [12 empty] | - | - | - | - | - | -
| 9.c.4 | Support in training newly hired FMS CSC system users and other Super users in the devolved MDA's (HR Directors) on HRMIS users. | All FMS Civil Servant | HR and CS Adviser, Systems Adviser and Training Specialist, ICT Adviser, Vendor System expert. | 4.2 | Very High | High |  | Medium | [12 empty] | - | - | - | - | - | -
| 9.e | Monitoring and Evaluation
| 9.e.1 | Conduct M&E Edline Assessment using PEFA, TADAT, MAPS, and HR/CS methodology | All FMS | Competitive procurement by PREMIS, Procurement Adviser | 2.4 | Very High |  | Very High | High
Intergovernmental Fiscal Relationships
| 10 | Support to State Position
| 10.a | Support to State Position
Removed and change to TA if asked by FMS | 10.a.1 | Meeting with FGS to discuss funding, reporting requirements | FGS/Treasury, FMS | Meeting | 3.1 | High |  | Very High | [13 empty] | - | - | - | - | - | -
Removed and can be included in the Quarterly meetings with Ministers | 10.a.2 | Briefing for Ministers for Finance and Senior MoF officials on IGFR, Federalism. | All FMS MoF | Workshop. PREMIS Advisers as required | 3.1 | Very High |  | Very High | [13 empty] | - | - | - | - | - | -
| 10.a.3 | Support on IGFR policies and strategies to engage with FGS and other States in National Discussion Forums. | All FMS MoF | Ongoing TA | 3.1 | Very High | [15 empty] | - | - | - | - | - | -
| 10.a.4 | Support on policies and engagement with National Forums on Natural Resource Taxation. | All FMS MoF | Ongoing TA | 3.1 | Very High | [15 empty] | - | - | - | - | - | -
[25 empty] | CAT 1 | CAT 2 | CAT 3
[22 empty] | 16 |  |  | 54 | 42 | 8
104
16
[24 empty] | Nairobi | State Based
[25 empty] | CAT 1 | CAT 2 | CAT 3
[24 empty] | 16 | 54 | 42 | 8
104
|  | Output | Nairobi/Addis-based Workshop | Category 1 - Structured Mentoring | Category 2 - Separate Workshop | Category 3 - Combined Workshop
|  | 1 | 2 | 16 | 26 | 3
|  | 2 | 5 | 10 | 4 | 3
|  | 3 | 3 | 20 | 2 | 0
|  | 4 | 7 | 8 | 10 | 2
|  |  | 17 | 54 | 42 | 8
|  | FMS | Nairobi/Addis-based Workshop | Category 1 - Structured Mentoring | Category 2 - Separate Workshop | Category 3 - Combined Workshop
|  | HSS |  | 15 | 11
|  | GSS |  | 12 | 12
|  | JSS |  | 15 | 9
|  | SWS |  | 12 | 10
|  |  |  | 54 | 42 | 0
|  | Total Number of Workshops |  | 50 | 46 | 8
104